## IMPLEMENTATION PLAN_CONSOLIDAT
TOPIC | ITEM | CMMP initiative | A# | Action activities | Ownership | Implementing Arm | Secretariat's Comments | Stakeholders' comments | Year 0 | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 6 |  | Year 7 |  | Year 8 |  | Year 9 |  | Year 10
[9 empty] | H2 2021 | H1 2022 | H2 2022 | H1 2023 | H2 2023 | H1 2024 | H2 2024 | H1 2025 | H2 2025 | H1 2026 | H2 2026 | H1 2027 | H2 2027 | H1 2028 | H2 2028 | H1 2029 | H2 2029 | H1 2030 | H2 2030 | H1 2031 | H2 2031
Formation | F1.1 | Governance of CMMP |  | Adopt the Strategy and Roadmap as an official Implemetation Effort under 8NDP and future plans and commit to a 10 year programme of reforms, with an emphasis to complete key reforms in the first 2 years | Cabinet/MoF
Formation | F1.2 | Governance of CMMP |  | Transform the current Steering Committee ("SC") to oversee implementation of the Roadmap. The SC will be led by the Minister of Finance's Office and deputised by the Minister of National Planning's Office. Other members to comprise of the heads of the following institutions: * Securities and Exchange Commission * Bank of Zambia * Pensions and Insurance Authority * Zambia Rvenue Authority * Zambia Dvelopment Agency * Capital Markets Association of Zambia * Lusaka Securities Exchange Plc * National Pensions Scheme Authority * National Health Insurance Management Authority *Banker's Association of Zambia | Cabinet/MoF
Formation | F1.3 | Governance of CMMP |  | Mandate the Capital Markets Working Group (under the National Financial Inclusion Strategy) to become the Implementation arm [Restructure the current composition] | Cabinet/MoF
Formation | F1.4 | Governance of CMMP |  | Create the Secretariat for the Capital Markets Working Group (CMWG) outside the civil Service remuneration structure and locate it at SEC or MOF (ref: RuFep) | Cabinet/MoF
Formation | F1.5 | Governance of CMMP |  | Create 5 Action Teams for the following areas of effort: * Fiscal policies to address crowding-out effect and other policies to support development of the local capital markets * Choice international investment destination [key deliverables is to secure MSCI rating (ToRs on p6) and propose financial hub model - reMauritus/Abu Dhabi/Seychelles. etc] * Changes to SEC funding model and enhance capacity for SEC to be able to achieve full functionality required under the CMMP * Product Development * Capacity Building [regulators,market players, investing public, etc] | Cabinet/MoF
Formation | F1.6 | Governance of CMMP |  | Seek donor support for financing and staffing | MoF/CMWG
Formation | F1.7 | Governance of CMMP |  | Orientation and development of the Monitoring & Evaluation Framework: * Orientation walk-through of the CMMP * Monitoring & Evaluation Framework development and capacity building programme | CMWG/MoF*
Formation | F1.8 | Governance of CMMP |  | Sensitisation programme/workshop of CMMP to Implementing Partners (includes members of the Action Teams & institutions with assigned tasks in CMMP) | CMWG
Formation | F1.9 | Governance of CMMP |  | Develop detailed workplans & budgets for the various broad tasks in the Implementation Plan | CMWG/Action Teams
Formation | F1.10 | Governance of CMMP |  | Create and maintain a database consisting of capital markets benchmark data to measure implementation impact and progress | CMWG
Formation | F1.11 | Governance of CMMP |  | Report implementation progress to the SC quarterly & to Cabinet* | CMWG/MoF*
Formation | F1.12 | Governance of CMMP |  | Evaluate Roadmap progress annually and involve external evaluators at end of years 2, 4, 6, 8 and 10 | CMWG
CMMP ACTIVITIES | [8 empty] | Year 0 | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 6 |  | Year 7 |  | Year 8 |  | Year 9 |  | Year 10
[9 empty] | H2 2021 | H1 2022 | H2 2022 | H1 2023 | H2 2023 | H1 2024 | H2 2024 | H1 2025 | H2 2025 | H1 2026 | H2 2026 | H1 2027 | H2 2027 | H1 2028 | H2 2028 | H1 2029 | H2 2029 | H1 2030 | H2 2030 | H1 2031 | H2 2031
KEY
Action Team 1 (19 activities)
Action Team 2 ( 6 activities)
Action Team 3 (5 activities)
Action Team 4 (14 activities)
Action Team 5 (13 activities)
All teams to check (21 activities)
78 activities
Primary Bond Market | 1.1 | Effect changes to BoZ auction process to ensure transparency in line with international best practice | 1.1.1 | Update bond process regulations to mandate immediate reporting of auction results and winning yields | BoZ | Action Team 1
Primary Bond Market |  |  | 1.1.2 | Amend the Securities Act by including an explicit provision on the status of government bonds with respect to registration with the SEC | MoFNP / SEC / MoJ | Action Team 1
Secondary Bond Market | 1.2 | Creation of Benchmark Bonds | 1.2.1 | Finalise the updating of the issuance policy to align with benchmark bond building | MoFNP | Action Team 1
Secondary Bond Market | 1.3 | Create framework for appointing the banks as primary dealers | 1.3.1 | Identify suitable banks to act as market makers | MoFNP / BOZ | Action Team 1
Secondary Bond Market |  |  | 1.3.2 | Update regulations as necessary to appoint selected primary dealers | MoFNP / BOZ | Action Team 1
Secondary Bond Market |  |  | 1.3.3 | Communicate changes in compliance standards to banks | MoFNP, BOZ | Action Team 1
Secondary Bond Market | 1.4 | Enhance electronic government bond trading mechanism | 1.4.1 | Fully implement the electronic bond trading platform and benchmark against international best practice, i.e. other markets like South Africa | MoFNP/ BoZ | Action Team 1
Secondary Bond Market |  |  | 1.4.2 | Educate market participants on new platform and implement into market | MoFNP / BOZ | Action Team 5
Secondary Bond Market | 1.5 | Implementation of safe, efficient CSD including real DvP | 1.5.1 | Based on MAR findings, BoZ, SEC and LuSE to develop process for CSD enhancements, including DvP settlement | BOZ/SEC/LUSE | Action Team 2
Secondary Bond Market |  |  | 1.5.2 | Appoint consulting team to provide technical assistance on implementation of enhancements with a view to eventual consolidation | BOZ/SEC/LuSE | Action Team 2
Secondary Bond Market |  |  | 1.5.3. | Increase retail participation in secondary bond markets | MoF/BoZ/SEC | Action Team 2
Secondary Bond Market |  |  | 1.5.4 | Undertake study for rationalising of the LuSE and BoZ CSDs | MoF/BoZ/SEC | Action Team 2
Secondary Bond Market | 1.6 | Alter post-trade reporting requirements to enhance transparency | 1.6.1 | Review current reporting requirements and compare to international best practices on reporting | SEC/ /BOZ/ LuSE | Action Team 2
Secondary Bond Market |  |  | 1.6.2 | Identify gaps in current reporting requirements and implement changes in reporting requirements | SEC/ LuSE | Action Team 2
Corporate Bond Market | 2.1 | Develop and implement study on corporate bond dealing landscape | 2.1.1 | Conduct primary research across cross-sectional sample of businesses on their financing needs and reasons for lack of corporate bond activity | SEC / PIA | Action Team 4
Equity Markets | 2.2 | Making the market more attractive for issuers | 2.2.1 | Conduct roadshow with strategic sectors across SADC (including Zambia) to gather views and identify potential developments to improve issuing activity | ZDA/SEC/LUSE | Action Team 2 / Action Team 4
Equity Markets |  |  | 2.2.2 | Develop strategy based on views gathered in roadshow | ZDA/IDC/LUSE/CMAZ | Action Team 2 / Action Team 4
Equity Markets | 2.3 | Develop a pipeline of companies with long term equity and debt financing needs | 2.3.1 | Assemble task force in partnership with business associations to identify potential equity and debt listings and private placement opportunities | ZDA/ID/LUSE/CMAZ | Action Team 1 / Action Team 4
Equity Markets |  |  | 2.3.2 | Determine conditions for pipeline inclusion (e.g. revenue, ESG standards, largest taxation payers, etc.) and incentives | ZDA/IDC/LUSE/CMAZ | Action Team 1 / Action Team 2 / Action Team 4
Equity Markets |  |  | 2.3.3 | Identify and engage initial business for inclusion and launch pipeline | ZDA/IDC/ZACCI/CMAZ | Action Team 2 / Action Team 4
Equity Markets | 2.4 | Adjust LuSE listing requirements | 2.4.1 | Review current listing requirements compared to peer markets (e.g. profitability, years in business, ESG requirements, etc.) to identify gaps | LUSE | Action Team 1 / Action Team 2
Equity Markets |  |  | 2.4.2 | Develop adjustments and updates regulations as necessary to implement new listing requirements in order to attract more listings | LUSE/CMAZ | Action Team 1 / Action Team 2
Equity Markets |  |  | 2.4.3 | Review and adjust SEC requirements for registration of securities and introduce new requirements for SMEs | SEC | Action Team 1 / Action Team 2
Capacity - Investor | 2.5 | Enhance investor awareness of collective investment schemes to bolster uptake | 2.5.1 | Conduct demand assessment to determine additional demand for CIS from investor base | CMAZ | Action Team 4
Capacity - Investor |  |  | 2.5.2 | Conduct roadshow in order to promote uptake of CISs from pools of investor base where demand was gauged to be the strongest | CMAZ | Action Team 4
Capacity - Investor |  |  | 2.5.3 | Formulate a government-backed CIS | CMAZ | Action Team 4
Capacity - Regulator |  |  | 2.5.4 | Enhance current regulatory and corporate governance structures/ codes for the CIS Industry. | SEC | Action Team 1
Private Equity | 3.1 | Adjust regulatory provision for private equity | 3.1.1 | Adjust current regulation on private equity to set an appropriate minimum and maximum for private equity investment for both public and private sector pension funds | MOFNP/ PIA | Action Team 1
SME Funding | 3.2 | Explore the nascent space of establishing SME debt, equity and technical assistance funds | 3.2.1 | Establish task force to commit study on feasibility of SME debt, equity and technical assistance | MOFNP/MoSMED/ZDA/CMAZ/SEC | Action Team 4
SME Funding |  |  | 3.2.2 | Establish task force to consider the role of the capital markets in pursuing interventions identified in existing feasibility studies of SME debt/equity lines | MOFNP/MOSMED/ZDA/CMAZ/SEC | Action Team 4
CM developments-tracking | 3.3 | Convene committee to track capital market developments (crowdfunding, sandboxing) | 3.3.1 | Set up committee to review global capital market trends | SEC | Action Team 4
CM developments-tracking |  |  | 3.3.2 | Identify appropriate trends and implement trends into Zambian market | SEC | Action Team 4
CM developments-tracking |  |  | 3.3.3 | Undertake monitoring and evaluation | CMMP Secretariate/Committee | Action Team 4
Product development | 3.4 | Expand market product offering to expand number of assets available for investments | 3.4.1 | Assess demand for expanded number of asset classes in the market via surveys of both retail and institutional investors (e.g. introducing REITs, ETFs, retail bonds) | SEC/ PIA/MOFNP/MOLSS/ZRA | Action Team 4
Product development |  |  | 3.4.2 | Assess adequacy of current guidelines in allowing for these asset classes | SEC | Action Team 1
Product development |  |  | 3.4.3 | Expand product landscape and required guidelines based on demand and in line with MAR findings | SEC | Action Team 4 / Action Team 1
Securitisation and mortgage refinancing | 3.5 | Develop framework for securitisation and mortgage refinancing to improve liquidity | 3.5.1 | Conduct market assessment to gauge demand for securitisation and mortgage refinancing in private market in line with best practice | SEC / MOFNP | Action Team 4
Securitisation and mortgage refinancing |  |  | 3.5.2 | Develop framework and requisite capabilities for securitisation and mortgage refinancing | SEC / MOFNP | Action Team 1 / Action Team 4
Securitisation and mortgage refinancing |  |  | 3.5.3 | Conduct market sensitisation to raise profile and usage of securitisation and mortgage refinancing and implementation | SEC / MOFNP/MOSMED | Action Team 4
Green Bonds | 3.6 | Develop framework for issuance of securities to finance green bonds | 3.6.1 | Develop conditions and incentives for these securities in line with international body standards and environmental, social and governance (ESG) and International Capital Markets Association (ICMA) principles | MoFNP/ MOGEE/SEC/BOZ/PIA | Action Team 1 / Action Team 2
Green Bonds |  |  | 3.6.2 | Update regulations to provide a comprehensive framework for these instruments | SEC | Action Team 1 / Action Team 2
Green Bonds |  |  | 3.6.3 | Conduct roadshow and/or workshops with stakeholders to Introduce these instruments to the market | SEC/ CMAZ | Action Team 4
Green Bonds |  |  | 3.6.4 | Develop database/pipeline for green investable projects | CMAZ | Action Team 4
Green Bonds |  |  | 3.6.5 | Develop concept note on positioning Zambia as a preferred global green investment hub | MOFNP/MOGEE/SEC | Action Team 4
Capacity - Regulator | 4.1 | Develop ongoing capacity building for regulators based on international best practice | 4.1.1 | Leverage on existing reports and assessments that identify capacity gaps across regulators and put in place measures to effect necessary changes | MOFNP/BOZ/SEC | Action Team 5
Capacity - Regulator |  |  | 4.1.2 | Schedule and execute skills development programmes to ensure capacity building programmes are in line with international standards | MOFNP/BOZ/SEC | Action Team 5
Capacity - Regulator |  |  | 4.1.3 | Ensure built capacity is maintained through annual review and continued skills updates | MOFNP/ BOZ / SEC | Action Team 5
Funding -SEC | 4.2 | Strengthening the Securities and Exchange Commission | 4.2.1 | Review current SEC funding policy/model against its needs to identify shortfalls/shortcomings, and undertake a benchmark study with other regulators | MoFNP/ SEC | Action Team 3
Funding -SEC |  |  | 4.2.2 | Engage government and market players to develop updated SEC funding mechanism and implement taking into consideration findings under 4.2.1 | MoFNP/ SEC | Action Team 3
Funding -CMO | 4.3 | Develop new funding model for LuSE | 4.3.1 | Identify current shortcomings in funding models for various key market players such as exchanges, CSDs, brokerage firms, etc. | CMAZ/LUSE | Action Team 3
Funding -CMO |  |  | 4.3.2 | Determine scope for additional value addition services as revenue generators, e.g. publishing market research, information dissemination | CMAZ/LUSE | Action Team 3
Capacity - CMO |  |  | 4.3.3 | Implement additional value addition services and revise transaction fees (e.g. listing fees, trade commissions, annual fees) | CMAZ/LUSE | Action Team 3
Funding -CMO |  |  | 4.3.4 | Implement additional value addition services and revise listing and annual fees | LuSE/CMAZ/ALL | Action Team 3 / Action Team 1
Capacity - CMO | 4.4 | Develop broad-based capacity building initiatives | 4.4.1 | Commission study on best-practice for capacity building | SEC/ CMAZ | Action Team 5
Capacity - CMO |  |  | 4.4.2 | Identify gaps with existing capital market practitioners - including auditors, advocates, accountants, brokers, bankers, corporate financiers, financial journalists etc. through surveys, workshops | SEC/ CMAZ | Action Team 5
Capacity - CMO |  |  | 4.4.3 | Identify skills development programmes to bridge knowledge gap and partner with education provider to design curriculum | SEC/ CMAZ | Action Team 5
Capacity - CMO |  |  | 4.4.4 | Develop and execute schedule for participating in bridging knowledge gap | SEC/ CMAZ | Action Team 5
Capacity - CMO |  |  | 4.4.5 | Schedule and execute capacity building maintenance in order to update skills as required | SEC/ CMAZ | Action Team 5
Capacity - Investor | 4.5 | Develop and implement targeted investor education programme | 4.5.1 | Conduct study on public literacy and capital markets views to identify gaps in knowledge and develop educational material | SEC/CMAZ | Action Team 5
Capacity - Investor |  |  | 4.5.2 | Schedule and execute public programmes to deliver educational material | SEC/CMAZ | Action Team 5
Capacity - ALL |  | Establish an institute to facilitate capital markets specific courses | 4.6.1 | Establish an institute to facilitate capital markets specific courses | SEC and CMAZ | Action Team 5
|  |  | 4.6.2 | Establish a capital market training institute | SEC/CMAZ | Action Team 5
Capacity - Regulator | 5.1 | Streamline mandates of capital market regulators and communicate to market | 5.1.1 | Review existing regulatory mandates of the major regulatory stakeholders, including BoZ, SEC and MoFNP, and compare regulatory mandate to peer group | MOFNP/ BOZ / SEC | Action Team 1
Capacity - Regulator |  |  | 5.1.2 | Coordinate and consolidate regulatory mandate to ensure alignment, with possible implementation of the twin peaks model of regulation (stability and conduct) | MOFNP/ BOZ / SEC/PIA | Action Team 1
NAPSA - Investment Guidelines | 5.2 | Establish and update investment guidelines for NAPSA | 5.2.1 | Review which products are most appropriate for outsourcing in order to guide updated guidelines and opportunities for outsourcing fund management to private sector | MOFNP/MOLSS/NAPA/SEC | Action Team 1
NAPSA - Investment Guidelines |  |  | 5.2.2 | Aid in developing new investment guidelines based on study findings and update regulations in order to implement new guidelines | MOFNP/MOLSS/NAPSA/SEC | Action Team 1
NAPSA - Investment Guidelines |  |  | 5.2.3 | Implement framework for outsourcing fund management to private sector | MOFNP/MOLSS/NAPSA/SEC | Action Team 1
Investor protection | 5.3 | Strengthen regulatory protections afforded to minority shareholders | 5.3.1 | Adjust regulations as necessary - such as mandating appointment of independent directors to company boards, strengthening requirements around conflict of interest and allowing a group of minority shareholders to put items on the meeting agenda | SEC | Action Team 1
Investor protection |  |  | 5.3.2 | Communicate changes to market with timeframe for implementation | SEC | Action Team 1
Investor protection | 5.4 | Make protection of foreign investments explicit | 5.4.1 | Develop broad-based foreign investment policy based on international best practices | MOFNP/ ZDA | Action Team 1 / Action Team 2
Investor protection |  |  | 5.4.2 | Drive updated regulation to remove potential for nationalisation, e.g. through stronger property rights | MOFNP / ZDA | Action Team 1 / Action Team 2
Tax incentives | 5.5 | Adjust tax regime with potential incentives for businesses and investors in strategically important sectors | 5.5.1 | Identify strategically important sectors (e.g. based on contribution to GDP or diversification of the economy, such as agriculture, energy and tourism) | ZRA/MOFNP/ZDA/SEC | Action Team 1 / Action Team 2
Tax incentives |  |  | 5.5.2 | Develop tax incentives for identified sectors | ZRA | Action Team 1 / Action Team 2
Tax incentives |  |  | 5.5.3 | Update regulation to extend existing tax breaks in order to increase incoming capital flows | MOFNP/ZRA/ZDA/SEC | Action Team 1 / Action Team 2
Double Taxation Agreements | 5.6 | Review and develop DTA with key trading partners and opportunities for regional integration | 5.6.1 | Review existing DTA agreements | ZDA/MOFNP/ZRA | Action Team 1 / Action Team 2
|  |  | 5.6.2 | Identify gaps in current DTA agreements, giving precedence to developing DTA agreements with key trade partners | MOFNP/ZRA/ZDA | Action Team 1 / Action Team 2
Audited accounts | 5.7 | Develop guidelines for companies seeking long-term financing to prepare audited accounts | 5.7.1 | Provide guidelines on preparing audited accounts to assist limited liability companies with long-term financing compliance needs | SEC/MOFNP/ZICA | Action Team 1
Audited accounts |  |  | 5.7.2 | Host workshops to inform companies and their auditors about new framework/guidelines | SEC/MOFNP/ZICA | Action Team 1
Notes
Red | Short term initiative
Amber | Medium -term initiative
Green | Long-term initiative

## Action Teams-Consolidated
CMMP ACTION TEAM 1: FISCAL POLICIES | [6 empty] | Year 0 | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 6 |  | Year 7 |  | Year 8 |  | Year 9 |  | Year 10
[6 empty] | YES, NO, COMMENTS | H2 2021 | H1 2022 | H2 2022 | H1 2023 | H2 2023 | H1 2024 | H2 2024 | H1 2025 | H2 2025 | H1 2026 | H2 2026 | H1 2027 | H2 2027 | H1 2028 | H2 2028 | H1 2029 | H2 2029 | H1 2030 | H2 2030 | H1 2031 | H2 2031
CMMP Development Area 1: Enhancing the government bond market
Primary Bond Market | 1.1 | Effect changes to BoZ auction process to ensure transparency in line with international best practice | 1.1.1 | Update bond process regulations to mandate immediate reporting of auction results and winning yields | BoZ
|  |  | 1.1.2 | Amend the Securities Act by including an explicit provision on the status of government bonds with respect to registration with the SEC | MoFNP, SEC, MoJ
Secondary Bond Market | 1.2 | Creation of Benchmark Bonds | 1.2.1 | Finalise the updating of the issuance policy to align with benchmark bond building | MoFNP
| 1.3 | Create framework for appointing the banks as primary dealers | 1.3.1 | Identify suitable banks to act as market makers | MoFNP, BOZ
|  |  | 1.3.2 | Update regulations as necessary to appoint selected primary dealers | MoFNP, BOZ
|  |  | 1.3.3 | Communicate changes in compliance standards to banks | MoFNP, BOZ
| 1.4 | Enhance electronic government bond trading mechanism | 1.4.1 | Fully implement the electronic bond trading platform and benchmark against international best practice, i.e. other markets like South Africa | MoFNP/ BoZ
CMMP Development Area 2: Enhancing other traditional security markets
Equity Markets | 2.3 | Develop a pipeline of companies with long term equity and debt financing needs | 2.3.2 | Determine conditions for pipeline inclusion (e.g. revenue, ESG standards, largest taxation payers, etc.) and incentives | ZDA, IDC, LuSE, CMAZ
| 2.4 | Adjust LuSE listing requirements | 2.4.1 | Review current listing requirements compared to peer markets (e.g. profitability, years in business, ESG requirements, etc.) to identify gaps | LuSE
|  |  | 2.4.2 | Develop adjustments and updates regulations as necessary to effect implementation of new listing requirements in order to attract more listings | LuSE,CMAZ
|  |  | 2.4.3 | Review and adjust SEC requirements for registration of securities and introduce new requirements for SMEs | SEC
Capacity - Investor | 2.5 | Enhance investor awareness of collective investment schemes to bolster uptake | 2.5.4 | Enhance current regulatory and corporate governance structures/ codes for the CIS Industry. | SEC
CMMP Development Area 3: Development of new and innovative products/markets
Private Equity | 3.1 | Adjust regulatory provision for private equity | 3.1.1 | Adjust current regulation on private equity to set an appropriate minimum and maximum for private equity investment for both public and private sector pension funds | MOFNP/ PIA
Product development | 3.4 | Expand market product offering to expand number of assets available for investments | 3.4.2 | Assess adequacy of current guidelines in allowing for these asset classes | SEC
|  |  | 3.4.3 | Expand product landscape and required guidelines based on demand and in line with MAR findings | SEC
Securitisation and mortgage refinancing | 3.5 | Develop framework for securitisation and mortgage refinancing to improve liquidity | 3.5.2 | Develop framework and requisite capabilities for securitisation and mortgage refinancing
Green Bonds | 3.6 | Develop framework for issuance of securities to finance green bonds | 3.6.1 | Develop conditions and incentives for these securities in line with international body standards and environmental, social and governance (ESG) and International Capital Markets Association (ICMA) principles | MoFNP/ MoGEE/SEC/BoZ/PIA
|  |  | 3.6.2 | Update regulations to provide a comprehensive framework for these instruments | SEC
CMMP Development Area 4: Enhancemement of Capacity across the capital markets
Funding -SEC | 4.2 | Strengthening the Securities and Exchange Commission | 4.2.2 | Engage government and market players to develop updated SEC funding mechanism and implement taking into consideration findings under 4.2.1 | MoFNP/ SEC
Funding -CMO | 4.3 | Develop new funding model for LuSE | 4.3.4 | Implement additional value addition services and revise listing and annual fees | LuSE/CMAZ/ALL
CMMP Development Area 5: Enhancing the capital market regulatory environment
Capacity - Regulator | 5.1 | Streamline mandates of capital market regulators and communicate to market | 5.1.1 | Review existing regulatory mandates of the major regulatory stakeholders, including BoZ, SEC and MoFNP, and compare regulatory mandate to peer group | MOFNP/ BOZ / SEC / PIA
|  |  | 5.1.2 | Coordinate and consolidate regulatory mandate to ensure alignment, with possible implementation of the twin peaks model of regulation (stability and conduct) | MOFNP/ BOZ / SEC/PIA
NAPSA - Investment Guidelines | 5.2 | Establish and update investment guidelines for NAPSA | 5.2.1 | Review which products are most appropriate for outsourcing in order to guide updated guidelines and opportunities for outsourcing fund management to private sector | MOFNP / MoLSS/ NAPSA/ SEC
|  |  | 5.2.2 | Aid in developing new investment guidelines based on study findings and update regulations in order to implement new guidelines | MOFNP / MoLSS/ NAPSA/ SEC
|  |  | 5.2.3 | Implement framework for outsourcing fund management to private sector | MOFNP / MoLSS/ NAPSA/ SEC
Investor protection | 5.3 | Strengthen regulatory protections afforded to minority shareholders | 5.3.1 | Adjust regulations as necessary - such as mandating appointment of independent directors to company boards, strengthening requirements around conflict of interest and allowing a group of minority shareholders to put items on the meeting agenda | SEC
|  |  | 5.3.2 | Communicate changes to market with timeframe for implementation | SEC
Investor protection | 5.4 | Make protection of foreign investments explicit | 5.4.1 | Develop broad-based foreign investment policy based on international best practices | MOFNP / ZDA
|  |  | 5.4.2 | Drive updated regulation to remove potential for nationalisation, e.g. through stronger property rights | MOFNP / ZDA
Tax incentives | 5.5 | Adjust tax regime with potential incentives for businesses and investors in strategically important sectors | 5.5.1 | Identify strategically important sectors (e.g. based on contribution to GDP or diversification of the economy, such as agriculture, energy and tourism) | ZRA / MOFNP / ZDA /SEC
|  |  | 5.5.2 | Develop tax incentives for identified sectors | ZRA
|  |  | 5.5.3 | Update regulation to extend existing tax breaks in order to increase incoming capital flows | MOFNP/ZRA/ZDA/SEC
Double Taxation Agreements | 5.6 | Review and develop DTA with key trading partners and opportunities for regional integration | 5.6.1 | Review existing DTA agreements | ZDA/MOFNP/ZRA
|  |  | 5.6.2 | Identify gaps in current DTA agreements, giving precedence to developing DTA agreements with key trade partners | MOFNP/ZRA/ZDA
Audited accounts | 5.7 | Develop guidelines for companies seeking long-term financing to prepare audited accounts | 5.7.1 | Provide guidelines on preparing audited accounts to assist limited liability companies with long-term financing compliance needs | SEC/MOFNP/ZICA
|  |  | 5.7.2 | Host workshops to inform companies and their auditors about new framework/guidelines | SEC/MOFNP/ZICA
CMMP ACTION TEAM 2: CHOICE INTERNATIONAL INVESTMENT DESTINATION
CMMP Development Area 1: Enhancing the government bond market
Secondary Bond Market | 1.5 | Implementation of safe, efficient CSD including real DvP | 1.5.1 | Based on MAR findings, BoZ, SEC and LuSE to develop process for CSD enhancements, including DvP settlement | BOZ/SEC/LUSE
|  |  | 1.5.2 | Appoint consulting team to provide technical assistance on implementation of enhancements with a view to eventual consolidation | BOZ/SEC/LuSE
|  |  | 1.5.3 | Increase retail participation in secondary bond markets | MoF/BoZ/SEC
|  |  | 1.5.4 | Undertake study for rationalising of the LuSE and BoZ CSDs | MoF/BoZ/SEC
| 1.6 | Alter post-trade reporting requirements to enhance transparency | 1.6.1 | Review current reporting requirements and compare to international best practices on reporting | SEC/BOZ/LuSE
|  |  | 1.6.2 | Identify gaps in current reporting requirements and implement changes in reporting requirements | SEC/ LuSE
CMMP Development Area 2: Enhancing other traditional security markets
Equity Markets | 2.2 | Making the market more attractive for issuers | 2.2.1 | Conduct roadshow with strategic sectors across SADC (including Zambia) to gather views and identify potential developments to improve issuing activity | ZDA/SEC/LuSE
|  |  | 2.2.2 | Develop strategy based on views gathered in roadshow | ZDA/LuSE
| 2.3 | Develop a pipeline of companies with long term equity and debt financing needs | 2.3.1 | Assemble task force in partnership with business associations to identify potential equity and debt listings and private placement opportunities | ZDA/ IDC / LuSE / CMAZ
|  |  | 2.3.2 | Determine conditions for pipeline inclusion (e.g. revenue, ESG standards, largest taxation payers, etc.) and incentives | ZDA/IDC/LuSE/CMAZ
|  |  | 2.3.3 | Identify and engage initial business for inclusion and launch pipeline | ZDA/IDC/ZACCI/CMAZ
| 2.4 | Adjust LuSE listing requirements | 2.4.1 | Review current listing requirements compared to peer markets (e.g. profitability, years in business, ESG requirements, etc.) to identify gaps | LuSE
|  |  | 2.4.2 | Develop adjustments and updates regulations as necessary to implement new listing requirements in order to attract more listings | LUSE/CMAZ
|  |  | 2.4.3 | Review and adjust SEC requirements for registration of securities and introduce new requirements for SMEs | SEC
CMMP Development Area 3: Development of new and innovative products/markets
Green Bonds | 3.6 | Develop framework for issuance of securities to finance green bonds | 3.6.1 | Develop conditions and incentives for these securities in line with international body standards and environmental, social and governance (ESG) and International Capital Markets Association (ICMA) principles | MOFNP / MoGEE /SEC /BOZ / PIA
|  |  | 3.6.2 | Update regulations to provide a comprehensive framework for these instruments | SEC
|  |  | 3.6.3 | Conduct roadshow and/or workshops with stakeholders to Introduce these instruments to the market | SEC/ CMAZ
|  |  | 3.6.4 | Develop database for green investable projects | CMAZ
|  |  | 3.6.5 | Develop concept note on positioning Zambia as a preferred global green investment hub | MOFNP/MoGEE/SEC
CMMP Development Area 5: Enhancing the capital market regulatory environment
Investor protection | 5.4 | Make protection of foreign investments explicit | 5.4.1 | Develop broad-based foreign investment policy based on international best practices | MOFNP / ZDA
Investor protection |  |  | 5.4.2 | Drive updated regulation to remove potential for nationalisation, e.g. through stronger property rights | MOFNP / ZDA
Tax incentives | 5.5 | Adjust tax regime with potential incentives for businesses and investors in strategically important sectors | 5.5.1 | Identify strategically important sectors (e.g. based on contribution to GDP or diversification of the economy, such as agriculture, energy and tourism) | ZRA/MOFNP/ZDA
Tax incentives |  |  | 5.5.2 | Develop tax incentives for identified sectors | ZRA
Tax incentives |  |  | 5.5.3 | Update regulation to extend existing tax breaks in order to increase incoming capital flows | MOFNP/ZRA/ZDA/SEC
Double Taxation Agreements | 5.6 | Review exisiting DTA agreements | 5.6.1 | Review existing DTA agreements | ZDA/MOFNP/ZRA
|  |  | 5.6.2 | Identify gaps in current DTA agreements, giving precedence to developing DTA agreements with key trade partners | MOFNP/ZRA/ZDA
CMMP ACTION TEAM 3: SEC FUNDING MODEL
CMMP Development Area 4: Enhancement of Capacity across the capital markets
Funding -SEC | 4.2 | Strengthening the Securities and Exchange Commission | 4.2.1 | Review current SEC funding policy/model against its needs to identify shortfalls/shortcomings, and undertake a benchmark study with other regulators | MoFNP/ SEC
Funding -SEC |  |  | 4.2.2 | Engage government and market players to develop updated SEC funding mechanism and implement taking into consideration findings under 4.2.1 | MoFNP/SEC
Funding -CMO | 4.3 | Develop new funding model for LuSE | 4.3.1 | Identify current shortcomings in funding models for various key market players such as exchanges, CSDs, brokerage firms, etc. | CMAZ / LuSE
|  |  | 4.3.2 | Determine scope for additional value addition services as revenue generators, e.g. publishing market research, information dissemination | CMAZ / LuSE
|  |  | 4.3.3 | Implement additional value addition services and revise transaction fees (e.g. listing fees, trade commissions, annual fees) | CMAZ / LuSE
|  |  | 4.3.4 | Implement additional value addition services and revise listing and annual fees | LuSE/CMAZ/ALL
CMMP ACTION TEAM 4: PRODUCT DEVELOPMENT
CMMP Development Area 2: Enhancing other traditional security markets
Corporate Bond Market | 2.1 | Develop and implement study on corporate bond dealing landscape | 2.1.1 | Conduct primary research across cross-sectional sample of businesses on their financing needs and reasons for lack of corporate bond activity | SEC / PIA
Equity Markets | 2.2 | Making the market more attractive for issuers | 2.2.1 | ZDA, SEC and LuSE to conduct roadshow with strategic sectors across SADC (including Zambia) to gather views and identify potential developments to improve issuing activity | ZDA/SEC/LuSE
Equity Markets |  |  | 2.2.2 | Develop strategy based on views gathered in roadshow | ZDA/ LuSE
Equity Markets | 2.3 | Develop a pipeline of companies with long term equity and debt financing needs | 2.3.1 | Assemble task force in partnership with business associations to identify potential equity and debt listings and private placement opportunities | ZDA/ IDC/LuSE/CMAZ
Equity Markets |  |  | 2.3.2 | Determine conditions for pipeline inclusion (e.g. revenue, ESG standards, largest taxation payers, etc.) and incentives | ZDA/ IDC/LuSE/CMAZ
Equity Markets |  |  | 2.3.3 | Identify and engage initial business for inclusion and launch pipeline | ZDA/ IDC/ ZACCI/CMAZ
Capacity - Investor | 2.5 | Enhance investor awareness of collective investment schemes to bolster uptake | 2.5.1 | Conduct demand assessment to determine additional demand for CIS from investor base | CMAZ
Capacity - Investor |  |  | 2.5.2 | conduct roadshow in order to promote uptake of CISs from pools of investor base where demand was gauged to be the strongest | CMAZ
Capacity - Investor |  |  | 2.5.3 | Formulate a government-backed CIS | MOFNP
CMMP Development Area 3: Development of new and innovative products/markets
SME Funding | 3.2 | Explore the nascent space of establishing SME debt, equity and technical assistance funds | 3.2.1 | Establish task force to commit study on feasibility of SME debt, equity and technical assistance | MOFNP / MoSMED /ZDA / CMAZ / SEC
SME Funding |  |  | 3.2.2 | Establish task force to consider the role of the capital markets in pursuing interventions identified in existing feasibility studies of SME debt/equity lines | MOFNP/MoSMED/ZDA /CMAZ / SEC
CM developments-tracking | 3.3 | Convene committee to track capital market developments (crowdfunding, sandboxing) | 3.3.1 | Set up committee to review global capital market trends | SEC
CM developments-tracking |  |  | 3.3.2 | Identify appropriate trends and implement trends into Zambian market | SEC
CM developments-tracking |  |  | 3.3.3 | Undertake monitoring and evaluation | CMMP Secretariate / Committee
Product development | 3.4 | Expand market product offering to expand number of assets available for investments | 3.4.1 | Assess demand for expanded number of asset classes in the market via surveys of both retail and institutional investors (e.g. introducing REITs, ETFs, retail bonds, derivatives) | SEC/ PIA/MoFNP/MOLSS/ZRA
Product development |  |  | 3.4.3 | Expand product landscape and required guidelines based on demand and in line with MAR findings | SEC
Securitisation and mortgage refinancing | 3.5 | Develop framework for securitisation and mortgage refinancing to improve liquidity | 3.5.1 | Conduct market assessment to gauge demand for securitisation and mortgage refinancing in private market in line with best practice | SEC / MOFNP
Securitisation and mortgage refinancing |  |  | 3.5.3 | Conduct market sensitisation to raise profile and usage of securitisation and mortgage refinancing and implementation | SEC / MOFNP/MoSMED
Green Bonds |  |  | 3.6.3 | Conduct roadshow and/or workshops with stakeholders to Introduce these instruments to the market | SEC/ CMAZ
CMMP ACTION TEAM 5: CAPACITY BUILDING
CMMP Development Area 1: Enhancing the government bond market
Secondary Bond Market |  | Enhance electronic government bond trading mechanism | 1.4.2 | Educate market participants on new platform and implement into market | MoFNP / BOZ
CMMP Development Area 3: Development of new and innovative products/markets
Securitisation and mortgage refinancing |  | Develop framework for securitisation and mortgage refinancing to improve liquidity | 3.5.2 | Develop framework and requisite capabilities for securitisation and mortgage refinancing | SEC / MOFNP
CMMP Development Area 4: Enhancement of Capacity across the capital markets
Capacity - Regulator | 4.1 | Develop ongoing capacity building for regulators based on international best practice | 4.1.1 | Leverage on existing reports and assessments that identify capacity gaps across regulators and put in place measures to effect necessary changes | MoFNP/ BOZ/ SEC
Capacity - Regulator |  |  | 4.1.2 | MoFNP, BoZ and SEC to schedule and execute skills development programmes to ensure capacity building programmes are in line with international standards | MOFNP/ BOZ / SEC
Capacity - Regulator |  |  | 4.1.3 | Ensure built capacity is maintained through annual review and continued skills updates | MOFNP/ BOZ / SEC
Capacity - CMO | 4.4 | Develop broad-based capacity building initiatives | 4.4.1 | Commission study on best-practice for capacity building | SEC/ CMAZ
Capacity - CMO |  |  | 4.4.2 | Identify gaps with existing capital market practitioners (including auditors, advocates, accountants, brokers, bankers, corporate financiers, financial journalists, etc.) through surveys and workshops | SEC/ CMAZ
Capacity - CMO |  |  | 4.4.3 | Identify skills development programmes to bridge knowledge gap and partner with education provider to design curriculum | SEC/ CMAZ
Capacity - CMO |  |  | 4.4.4 | Develop and execute schedule for participating in bridging knowledge gap | SEC/ CMAZ
Capacity - CMO |  |  | 4.4.5 | Schedule and execute capacity building maintenance in order to update skills as required | SEC/ CMAZ
Capacity - Investor | 4.5 | Develop and implement targeted investor education programme | 4.5.1 | Conduct study on public literacy and capital markets views to identify gaps in knowledge and develop educational material | SEC/CMAZ
Capacity - Investor |  |  | 4.5.2 | Schedule and execute public programmes to deliver educational material | SEC
Capacity - ALL | 4.6.1 |  |  | Establish an institute to facilitate capital markets specific courses | SEC/CMAZ
| 4.6.2. |  |  | Establish a capital market training institute | SEC/CMAZ

## HIGH LEVEL GANT CHART (hidden)
IMPLEMENTATION TIMELINE FOR INITIATIVES TO ENHANCE TRADITIONAL SECURITIES MARKETS
|  |  |  | SHORT TERM |  |  | MEDIUM TERM |  |  | LONG TERM
Topic | Item | Action | Ownership | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Corporate Bond Markets | 2.1 | Develop and implement study on corporate bond dealing landscape | SEC | bar: LONG TERM 2027 to LONG TERM 2030
Corporate Bond Markets | 2.2 | Making the market more attractive for issuers | ZDA | bar: SHORT TERM 2021 to SHORT TERM 2023
Equity Markets | 2.3 | Develop a pipeline of companies with long term equity and debt financing needs | ZDA/ IDC | bar: SHORT TERM 2021 to SHORT TERM 2023
Collective Investment Schemes | 2.4 | Adjust LuSE listing requirements | LuSE | bar: MEDIUM TERM 2024 to MEDIUM TERM 2026
Collective Investment Schemes | 2.5 | Enhance investor awareness of collective investment schemes to bolster uptake | SEC | bar: MEDIUM TERM 2024 to MEDIUM TERM 2026

## FORMATION (hidden)
[5 empty] | Ownership | Secretariat's Comments | Stakeholders' Meeting (30 & 31.03.2021) Comments | Year 0 | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 6 |  | Year 7 |  | Year 8 |  | Year 9 |  | Year 10
TOPIC | ITEM | CMMP initiative | A# | Action activities |  |  |  | H2 2021 | H1 2022 | H2 2022 | H1 2023 | H2 2023 | H1 2024 | H2 2024 | H1 2025 | H2 2025 | H1 2026 | H2 2026 | H1 2027 | H2 2027 | H1 2028 | H2 2028 | H1 2029 | H2 2029 | H1 2030 | H2 2030 | H1 2031 | H2 2031
Formation | F1.1 | Governance of CMMP |  | Adopt the Strategy and Roadmap as an official Implemetation Effort under 8NDP and future plans and commit to a 10 year programme of reforms, with an emphasis to complete key reforms in the first 2 years | Cabinet/MoF
Formation | F1.2 | Governance of CMMP |  | Transform the current Steering Committee ("SC") to oversee implementation of the Roadmap. The SC will be led by the Minister of Finance's Office and deputised by the Minister of National Planning's Office. Other members to comprise of the heads of the following institutions: * Securities and Exchange Commission * Bank of Zambia * Pensions and Insurance Authority * Zambia Rvenue Authority * Zambia Dvelopment Agency * Capital Markets Association of Zambia * Lusaka Securities Exchange Plc * National Pensions Scheme Authority * National Health Insurance Management Authority *Banker's Association of Zambia | Cabinet/MoF
Formation | F1.3 | Governance of CMMP |  | Mandate the Capital Markets Working Group (under the National Financial Inclusion Strategy) to become the Implementation arm [Restructure the current composition] | Cabinet/MoF
Formation | F1.4 | Governance of CMMP |  | Create the Secretariat for the Capital Markets Working Group (CMWG) outside the civil Service remuneration structure and locate it at SEC or MOF (ref: RuFep) | Cabinet/MoF
Formation | F1.5 | Governance of CMMP |  | Create 5 Action Teams for the following areas of effort: * Fiscal policies to address crowding-out effect and other policies to support development of the local capital markets * Choice international investment destination [key deliverables is to secure MSCI rating (ToRs on p6) and propose financial hub model - reMauritus/Abu Dhabi/Seychelles. etc] * Changes to SEC funding model and enhance capacity for SEC to be able to achieve full functionality required under the CMMP * Product Development * Capacity Building [regulators,market players, investing public, etc] | Cabinet/MoF
Formation | F1.6 | Governance of CMMP |  | Seek donor support for financing and staffing | MoF/CMWG
Formation | F1.7 | Governance of CMMP |  | Orientation and development of the Monitoring & Evaluation Framework: * Orientation walk-through of the CMMP * Monitoring & Evaluation Framework development and capacity building programme | CMWG/MoF*
Formation | F1.8 | Governance of CMMP |  | Sensitisation programme/workshop of CMMP to Implementing Partners (includes members of the Action Teams & institutions with assigned tasks in CMMP) | CMWG
Formation | F1.9 | Governance of CMMP |  | Develop detailed workplans & budgets for the various broad tasks in the Implementation Plan | CMWG/Action Teams
Formation | F1.10 | Governance of CMMP |  | Create and maintain a database consisting of capital markets benchmark data to measure implementation impact and progress | CMWG
Formation | F1.11 | Governance of CMMP |  | Report implementation progress to the SC quarterly & to Cabinet* | CMWG/MoF*
Formation | F1.12 | Governance of CMMP |  | Evaluate Roadmap progress annually and involve external evaluators at end of years 2, 4, 6, 8 and 10 | CMWG

## 1. GRZ BOND MARKET-AS SUBMITTED (hidden)
[5 empty] | Ownership | Secretariat's Comments | Stakeholders' Meeting (30 & 31.03.2021) Comments | Year 0 | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 6 |  | Year 7 |  | Year 8 |  | Year 9 |  | Year 10
TOPIC | ITEM | CMMP initiative | A# | Action activities |  |  |  | H2 2021 | H1 2022 | H2 2022 | H1 2023 | H2 2023 | H1 2024 | H2 2024 | H1 2025 | H2 2025 | H1 2026 | H2 2026 | H1 2027 | H2 2027 | H1 2028 | H2 2028 | H1 2029 | H2 2029 | H1 2030 | H2 2030 | H1 2031 | H2 2031
Primary Bond Market | 1.1 | Effect changes to BoZ auction process to ensure transparency in line with international best practice | 1.1.1 | Update bond process regulations to mandate immediate reporting of auction results and winning yields | BoZ | Consultant to clarify international best practice including platforms and benchmarks | Adopted
Secondary Bond Market | 1.2 | Creation of Benchmark Bonds | 1.2.1 | Establish issuance policy to align with benchmark bond building | MoF | Document to include work in progress | Adopted
Secondary Bond Market | 1.3 | Create framework for appointing the banks as primary dealers | 1.3.1 | Identify suitable banks to act as market makers | MoF | Document to recognise work in progress and consultant to recommend best practice. Refer to BoZ ETP | Need to include BoZ on ownership.
Secondary Bond Market |  |  | 1.3.2 | Update regulations as necessary | MoF |  | BoZ to be included in this activity.
Secondary Bond Market |  |  | 1.3.3 | Communicate changes in compliance standards to banks | MoF |  | Need to include BoZ on ownership.
Secondary Bond Market | 1.4 | Develop and implement electronic government bond trading mechanism | 1.4.1 | Engage consultant to develop electronic bond trading platform. Benchmark against other markets like South Africa (addition) | MoF | (1)Replace "Implementation" with "Enhancement" (2) Include BoZ, LuSE and SEC on ownership. | Need to include LuSE and SEC in the processes. Include benchmarking against international best practice e.g. practice in South Africa where MoF, Central Bank, exchange and CSD are all involved in the process.
Secondary Bond Market |  |  | 1.4.2 | Educate market participants on new platform and implement into market | MoF |  | Include boZ, LuSE and SEC on ownership
Secondary Bond Market | 1.5 | Implementation of safe, efficient CSD including real DvP | 1.5.1 | Based on MAR findings, BoZ to develop process for CSD enhancements, including DvP settlement | BoZ |  | Adopted
Secondary Bond Market |  |  | 1.5.2 | Appoint consulting team to provide technical assistance on implementation of enhancements with a view to eventual consolidation | BoZ |  | Include LuSE who are managing the other CSD. Include SEC on ownership.
[6 empty] | (1)Include new activity 1.5.3 "Increase retail participation in secondary bond markets" to be owned by MoF/BoZ/SEC (2) Include an activity 1.5.4 "to undertake study for rationalising of the LuSE and BoZ CSDs" | Include the market in this activity. SEC to be included on ownership. In addition, needs more clarity on ownership of second activity. However proposal was adopted.
Secondary Bond Market | 1.6 | Alter post-trade reporting requirements to enhance transparency | 1.6.1 | Review current reporting requirements and compare to international best practices on reporting | SEC/ LuSE | Include BoZ as part of ownership | This should be fused with the ETP.
Secondary Bond Market |  |  | 1.6.2 | Identify gaps in current reporting requirements and implement changes in reporting requirements | SEC/ LuSE |  | Adopted
| 1.7 |  |  |  | MoF/SEC | Proposal to change law to enable government securities to be registered and thereby enable any lacunas to be addressed. (If the bonds are listed, they must have first been registered). | New introduction
[6 empty] | Comment | Need to distinguish between organisations that will own and be responsible for the process and and those that will be part of the process.
[6 empty] | Comment | Need to look at the cost structure of the processes under this section.

## 2.ENHANCING TRADITIONAL MKTS (hidden)
[5 empty] | Ownership | Secretariat's Comments | Stakeholders' Meeting (30 & 31.03.2021) Comments | Year 0 | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 6 |  | Year 7 |  | Year 8 |  | Year 9 |  | Year 10
TOPIC | ITEM | CMMP initiative | A# | Action activities |  |  |  | H2 2021 | H1 2022 | H2 2022 | H1 2023 | H2 2023 | H1 2024 | H2 2024 | H1 2025 | H2 2025 | H1 2026 | H2 2026 | H1 2027 | H2 2027 | H1 2028 | H2 2028 | H1 2029 | H2 2029 | H1 2030 | H2 2030 | H1 2031 | H2 2031
Corporate Bond Market | 2.1 | Develop and implement study on corporate bond dealing landscape | 2.1.1 | Conduct primary research across cross-sectional sample of businesses on their financing needs and reasons for lack of corporate bond activity | SEC | Propose change to 2.1.1 to "SEC to commission a study… to inform the MoF on the financing needs of businesses in Zambia and affordable cost of capital. The Study should propose strategies for the MoF to consider including Policy changes aimed at addressing the crowding out effect of of government borrowing." | Proposal that the study include an aspect of looking at asset allocations in the Investment guidelines issued by PIA
Equity Markets | 2.2 | Making the market more attractive for issuers | 2.2.1 | Conduct roadshow with strategic sectors across SADC to gather views and identify potential developments to improve issuing activity | ZDA | 1) Include LuSE under ownership 2) recast across "SADC" to "Across regional and international markets/ platforms" 3) Consultants to clarfify why they included Zambia in the roadshow seeing that it is part of SADC. | Agreed
Equity Markets |  |  | 2.2.2 | Develop strategy based on views gathered in roadshow | ZDA | Include LuSE under the ownership | Agreed
Equity Markets | 2.3 | Develop a pipeline of companies with long term equity and debt financing needs | 2.3.1 | Assemble task force in partnership with business associations to identify potential equity and debt listings and private placement opportunities | ZDA/ IDC | Include CMAZ under the ownership | Proposal that the ZACCI should be included on the task force
Equity Markets |  |  | 2.3.2 | Determine conditions for pipeline inclusion (e.g. revenue, ESG standards, largest taxation payers, etc.) and incentives |  | Include CMAZ under the ownership | Agreed
Equity Markets |  |  | 2.3.3 | Identify and engage initial business for inclusion and launch pipeline |  | Include CMAZ under the ownership | Consider taking into account the revision of the listing requirement so that the two activities are done parallel to each other
Equity Markets | 2.4 | Adjust LuSE listing requirements | 2.4.1 | Review current listing requirements compared to peer markets (e.g. profitability, years in business, ESG requirements, etc.) to identify gaps | LUSE/CMAZ |  | Change timeline of this activity to short term
Equity Markets |  |  | 2.4.2 | Develop adjustments and updates regulations as necessary to effect implementation of new listing requirements in order to attract more listings | LUSE/CMAZ |  | Agreed
[5 empty] | SEC |  | Proposed new activity - review and adjust SEC registration requirements and introduce new requirements for SMEs - Access to information
Capacity - Investor | 2.5 | Enhance investor awareness of collective investment schemes to bolster uptake | 2.5.1 | Conduct demand assessment to determine additional demand for CIS from investor base | SEC | Replacement ownership for activity with CMAZ to encourage private sector to drive this activity. | Agreed
Capacity - Investor |  |  | 2.5.2 | Conduct roadshow in order to promote uptake for CIS from pools of investor base where demand was gauged to be the strongest | SEC | Replacement ownership for activity with CMAZ to encourage private sector to drive this activity. | Agreed
Capacity - Investor | [5 empty] | 2.5.3 - propose an activity to be owned by MoF/ SEC for the formation of a government backed CIS targeting institutions/ pools of funds such as ZAF who run savings/ credit unions and encourage them to invest in existing CISs or the GRZ Backed CIS | Agreed. Need to refine/think through
[6 empty] | 2.5.4 - Propose activity - SEC to enhance current regulatory and corporate governance structures/ codes for the CIS Industry. | Agreed

## 3. DEVELOP NEW PRODUCTS (hidden)
[5 empty] | Ownership | Secretariat's Comments | Stakeholders' Meeting (30 & 31.03.2021) Comments | Year 0 | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 6 |  | Year 7 |  | Year 8 |  | Year 9 |  | Year 10
TOPIC | ITEM | CMMP initiative | A# | Action activities |  |  |  | H2 2021 | H1 2022 | H2 2022 | H1 2023 | H2 2023 | H1 2024 | H2 2024 | H1 2025 | H2 2025 | H1 2026 | H2 2026 | H1 2027 | H2 2027 | H1 2028 | H2 2028 | H1 2029 | H2 2029 | H1 2030 | H2 2030 | H1 2031 | H2 2031
Private Equity | 3.1 | Adjust regulatory provision for private equity | 3.1.1 | Adjust current regulation on private equity to set an appropriate minimum and maximum for private equity investment for both public and private sector pension funds | MOF |  | PIA to be included under ownership. Clarification was also given that Napsa falls under PIA
SME Funding | 3.2 | Explore the nascent space of establishing SME debt, equity and technical assistance funds | 3.2.1 | Establish task force to commit study on feasibility of SME debt, equity and technical assistance | ZDA |  | Include other association such as CMAZ and MoF under onwership
proposed activity - Establish taskforce to consider the role of the Capital Markets in pursuing interventions identified in existing feasibility studies of SME debt/equity lines
CM developments-tracking | 3.3 | Convene committee to track capital market developments (crowdfunding, sandboxing) | 3.3.1 | Set up committee to review global capital market trends | SEC |  | Agreed
CM developments-tracking |  |  | 3.3.2 | Identify appropriate trends and implement trends into Zambian market | SEC |  | Ownership to change to Secretariat/task team looking into product development
proposed activity - Include monitoring and evaluation to be done by the Secretariat/CMMP Committee
Product development | 3.4 | Expand market product offering to expand number of assets available for investments | 3.4.1 | Assess demand for expanded number of asset classes in the market via surveys of both retail and institutional investors (e.g. introducing REITs, ETFs, retail bonds) | SEC |  | Include PIA, MoF and ZRA on ownership. Also include derivatives (also take into account warehouse receipts). Comment that something should be done to ensure that pension funds are brought on board specific to ETFs.
Product development |  |  | 3.4.2 | Assess adequacy of current guidelines in allowing for these asset classes | SEC |  | Agreed
Product development |  |  | 3.4.3 | Expand product landscape and required guidelines based on demand and in line with MAR findings | SEC |  | Agreed
Securitisation and mortgage refinancing | 3.5 | Develop framework for securitisation and mortgage refinancing to improve liquidity | 3.5.1 | Conduct market assessment to gauge demand for securitisation and mortgage refinancing in private market in line with best practice | SEC / MOF |  | Agreed
Securitisation and mortgage refinancing |  |  | 3.5.2 | Develop framework and requisite capabilities for securitisation and mortgage refinancing | SEC / MOF |  | is there need to develop a securitization framework?
Securitisation and mortgage refinancing |  |  | 3.5.3 | Conduct market sensitisation to raise profile and usage of securitisation and mortgage refinancing and implementation | SEC / MOF |  | Agreed
|  |  | 3.5.4 |  | SEC/IDC/MoF |  | Proposed activity - Undertake study to consider pros and cons of a soverign wealth fund. Comment that the team checks with other jurisdictions that have this, on who contributes to this fund
Green Bonds | 3.6 | Develop framework for issuance of securities to finance green bonds | 3.6.1 | Develop conditions and incentives for these securities in line with international body standards and environmental, social and governance (ESG) and International Capital Markets Association (ICMA) principles | MoF/ SEC/ CMAZ/ LUSE |  | LuSE to be included on the ownership
Green Bonds |  |  | 3.6.2 | Update regulations to provide a comprehensive framework for these instruments | SEC |  | Agreed
Green Bonds |  |  | 3.6.3 | Conduct roadshow and/or workshops with stakeholders to Introduce these instruments to the market | SEC/ CMAZ |  | Agreed
|  |  | 3.6.4 |  | CMAZ |  | Develop database/pipeline for green investable projects

## 4. ENHANCE CAPACITY (hidden)
[6 empty] | Ownership | Secretariat's Comments | Stakeholders' Meeting (30 & 31.03.2021) Comments | Year 0 | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 6 |  | Year 7 |  | Year 8 |  | Year 9 |  | Year 10
TOPIC | ITEM | CMMP initiative | A# | Action activities |  |  |  |  | H2 2021 | H1 2022 | H2 2022 | H1 2023 | H2 2023 | H1 2024 | H2 2024 | H1 2025 | H2 2025 | H1 2026 | H2 2026 | H1 2027 | H2 2027 | H1 2028 | H2 2028 | H1 2029 | H2 2029 | H1 2030 | H2 2030 | H1 2031 | H2 2031
Capacity - Regulator | 4.1 | Develop ongoing capacity building for regulators based on international best practice | 4.1.1 | Conduct workshop to identify capacity gaps across regulators | Conduct workshop to identify capacity gaps across regulators | MoF/ SEC/ CMAZ | Change to a study | Implement findings of the instituitonal assesment report
Capacity - Regulator |  |  | 4.1.2 | Schedule and execute skills development programmes and/or capacity building workshops with international regulators | Schedule and execute skills development programmes and/or capacity building programs with IOSCO, CISNA, Toronto Center, Community of SADC Stock Exchanges, African Securities Exchanges Association and any other reputable organization | MOF/ BOZ / SEC |  | Benchmark ourselves against a market that we aspire to level up to. Leverage on international standards setting organizations
Capacity - Regulator |  |  | 4.1.3 | Ensure built capacity is maintained through annual review and continued skills updates | Ensure built capacity is maintained through annual review and continued skills updates | MOF/ BOZ / SEC |  | Adopted as is
Funding -SEC | 4.2 | Strengthening the Securities and Exchange Commission | 4.2.1 | Review current SEC funding policy against its needs and identify shortfall | Review current SEC funding policy against its needs and identify shortfall | MoF/ SEC | Include a study/benchmark with other regulator models - pros & Cons | Adopted secretariates proposal
Funding -SEC |  |  | 4.2.2 | Engage government and market players to develop updated SEC funding mechanism and implement | Engage government and market players to develop updated SEC funding mechanism and implement | MoF/ SEC |  | based on findings of study proposed above
Funding -CMO | 4.3 | Develop new funding model for LuSE | 4.3.1 | Identify current shortfall in LuSE funding model | Identify current shortfall in funding model of specific projects/products | LuSE/CMAZ/ALL | Propose a wider view of looking at key stakeholders ( Brokers, CRA, Other exchanges) | change proposed by Secretariat adopted and emphasis made on the need to be market/product specific. Change ownership to CMAZ , LuSE & CRAs*
Funding -CMO |  |  | 4.3.2 | Determine scope for additional value addition services as revenue generators, e.g. publishing market research, information dissemination | Determine scope for additional value addition services as revenue generators | LuSE/CMAZ/ALL |  | Rec-casted to exclude the examples
Capacity - CMO |  |  | 4.3.3 | Develop required capacity to implement identified value addition services | Develop required capacity to implement identified value addition services | LuSE/CMAZ/ALL |  | Adopt same ownership as above
Funding -CMO |  |  | 4.3.4 | Implement additional value addition services and revise listing and annual fees | Implement additional value addition services and revise listing and annual fees | LuSE/CMAZ/ALL |  | Adopted as is
Capacity - CMO | 4.4 | Develop broad-based capacity building initiatives | 4.4.1 | Commission study on best-practice for capacity building | Commission study on best-practice for capacity building | SEC/ CMAZ | re-cast and state specific areas - Secretariate withdrew their proposal
Capacity - CMO |  |  | 4.4.2 | Identify gaps with existing capital market practitioners - including auditors, advocates, accountants, brokers, bankers, corporate financiers, financial journalists etc. through surveys, workshops | Identify gaps with existing capital market practitioners - including auditors, advocates, accountants, brokers, bankers, corporate financiers, financial journalists etc. through surveys, workshops | SEC/ CMAZ |  | Adopt as is
Capacity - CMO |  |  | 4.4.3 | Identify skills development programmes to bridge knowledge gap and partner with education provider to design curriculum fit for purpose | Identify skills development programmes to bridge knowledge gap and partner with education provider to design curriculum fit for purpose | SEC/ CMAZ |  | Adopt as is
Capacity - CMO |  |  | 4.4.4 | Develop and execute schedule for participating in bridging knowledge gap | Develop and execute schedule for participating in bridging knowledge gap | SEC/ CMAZ |  | Adopted but recaste to include strategising around securing sponsors for some programmes
Capacity - CMO |  |  | 4.4.5 | Schedule and execute capacity building maintenance in order to update skills as required | Schedule and execute capacity building maintenance in order to update skills as required | SEC/ CMAZ |  | Adopt as is
Capacity - Investor | 4.5 | Develop and implement targeted investor education programme | 4.5.1 | Conduct study on public literacy and capital markets views to identify gaps in knowledge and develop educational material | Conduct study on public literacy and capital markets views to identify gaps in knowledge and develop educational material | SEC/CMAZ | Include other players, not just SEC. SEC best placed as lead provided they have capacity built | Include CMAZ
Capacity - Investor |  |  | 4.5.2 | Schedule and execute public workshops to deliver training material | Schedule and execute public programs to deliver training material | SEC |  | Include CMAZ. Change from workshops to programme
Capacity - ALL |  | Establish an institute to facilitate capital markets specific courses |  | Establish an institute to facilitate capital markets specific courses |  | SEC and CMAZ |  | Adopted

## 5. ENHANCE REGULATORY ENVIR. (hidden)
[5 empty] | Ownership | Secretariat's Comments | Stakeholders' Meeting (30 & 31.03.2021) Comments | Year 0 | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 6 |  | Year 7 |  | Year 8 |  | Year 9 |  | Year 10
TOPIC | ITEM | CMMP initiative | A# | Action activities |  |  |  | H2 2021 | H1 2022 | H2 2022 | H1 2023 | H2 2023 | H1 2024 | H2 2024 | H1 2025 | H2 2025 | H1 2026 | H2 2026 | H1 2027 | H2 2027 | H1 2028 | H2 2028 | H1 2029 | H2 2029 | H1 2030 | H2 2030 | H1 2031 | H2 2031
Capacity - Regulator | 5.1 | Streamline mandates of capital market regulators and communicate to market | 5.1.1 | Review existing regulatory mandates of the major regulatory stakeholders, including BoZ, SEC and MoF and compare regulatory mandate to peer group | MOF/ BOZ / SEC |  | Include the PIA in the ownership section.
Capacity - Regulator |  |  | 5.1.2 | Coordinate and consolidate regulatory mandate to ensure alignment, with possible implementation of the twin peaks model of regulation (stability and conduct) | MOF/ BOZ / SEC |  | Include the PIA in the ownership section.
NAPSA - Investment Guidelines | 5.2 | Establish and update investment guidelines for NAPSA | 5.2.1 | Review which products are most appropriate for outsourcing in order to guide updated guidelines and opportunities for outsourcing fund management to private sector | MOF |  | Broaden this to include other entities like LASF, PSPF, Workers Com etc. Revision of PIA investment guidelines was underway. Need to explore the possibility of incorporating the discussions in the CMMP into the guidelines before they are finalised.
NAPSA - Investment Guidelines |  |  | 5.2.2 | Aid in developing new investment guidelines based on study findings and update regulations in order to implement new guidelines | MOF |  | Adopted
NAPSA - Investment Guidelines |  |  | 5.2.3 | Implement framework for outsourcing fund management to private sector | MOF |  | Adopted
Investor protection | 5.3 | Strengthen regulatory protections afforded to minority shareholders | 5.3.1 | Adjust regulations as necessary - such as mandating appointment of independent directors to company boards, strengthening requirements around conflict of interest and allowing a group of minority shareholders to put items on the meeting agenda | SEC |  | Adopted
Investor protection |  |  | 5.3.2 | Communicate changes to market with timeframe for implementation | SEC |  | Adopted
Investor protection | 5.4 | Make protection of foreign investments explicit | 5.4.1 | Develop broad-based foreign investment policy based on international best practices | MOF / ZDA |  | Adopted
Investor protection |  |  | 5.4.2 | Drive updated regulation to remove potential for nationalisation, e.g. through stronger property rights | MOF / ZDA |  | Adopted
Tax incentives | 5.5 | Adjust tax regime with potential incentives for businesses and investors in strategically important sectors | 5.5.1 | Identify strategically important sectors (e.g. based on contribution to GDP or diversification of the economy, such as agriculture, energy and tourism) | ZRA |  | Include MoF as they provide policy direction regarding taxes. ZDA and SEC must also be included.
Tax incentives |  |  | 5.5.2 | Develop tax incentives for identified sectors | ZRA |  | Include MoF as they provide policy direction regarding taxes. ZDA and SEC must also be included.
Tax incentives |  |  | 5.5.3 | Update regulation to extend existing tax breaks in order to increase incoming capital flows | ZRA |  | Include MoF as they provide policy direction regarding taxes. ZDA and SEC must also be included.
Double Taxation Agreements | 5.6 | Review and develop DTA with key trading partners and opportunities for regional integration | 5.6.1 | Review existing DTA agreements | ZDA |  | Include MoF and ZRA to the ownership section of this activity. Consideration to extend relief for dual listed firms.
|  |  | 5.6.2 | Identify gaps in current DTA agreements, giving precedence to developing DTA agreements with key trade partners | ZDA |  | Include MoF and ZRA to the ownership section of this activity. Consideration to extend relief for dual listed firms.
Audited accounts | 5.7 | Develop guidelines for companies seeking long-term financing to prepare audited accounts | 5.7.1 | Provide guidelines on preparing audited accounts to assist limited liability companies with long-term financing compliance needs | SEC / MOF |  | Include ZICA in the ownership section of this activity. They should lead this activity. This seems to speak to creation of a framework for the accountants in the firms and their auditors.
Audited accounts |  |  | 5.7.2 | Host workshops to inform companies about auditing guidelines | SEC / MOF |  | Change to read, "inform companies and their auditors on new framework/guidelines".

## Sheet1 (hidden)
CAPITAL MARKETS MASTER PLAN
Implementation Roadmap for Zambia |  |  | 2000000
2400000
|  |  |  | Secretariat's Comments | Stakeholders' Meeting (30 & 31.03.2021) Comments |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Year 5 |  | Year 6 |  | Year 7 |  | Year 8 |  | Year 9 |  | Year 10
Topic | Item | Action | Ownership |  |  | H2 2021 | H1 2022 | H2 2022 | H1 2023 | H2 2023 | H1 2024 | H2 2024 | H1 2025 | H2 2025 | H1 2026 | H2 2026 | H1 2027 | H2 2027 | H1 2028 | H2 2028 | H1 2029 | H2 2029 | H1 2030 | H2 2030 | H1 2031 | H2 2031 | KPI
Formation | F1 | Adopt the Strategy and Roadmap as an official Implemetation Effort under 8NDP and future plans and commit to a 10 year programme of reforms, with an emphasis to complete key reforms in the first 2 years | Cabinet/MoF
Formation | F2 | Transform the current Steering Committee ("SC") to oversee implementation of the Roadmap. The SC will be led by the Minister of Finance's Office and deputised by the Minister of National Planning's Office. Other members to comprise of the heads of the following institutions: * Securities and Exchange Commission * Bank of Zambia * Pensions and Insurance Authority * Zambia Rvenue Authority * Zambia Dvelopment Agency * Capital Markets Association of Zambia * Lusaka Securities Exchange Plc * National Pensions Scheme Authority * National Health Insurance Management Authority *Banker's Association of Zambia | Cabinet/MoF
Formation | F3 | Mandate the Capital Markets Working Group (under the National Financial Inclusion Strategy) to become the Implementation arm [Restructure the current composition] | Cabinet/MoF
Formation | F4 | Create the Secretariat for the Capital Markets Working Group (CMWG) outside the civil Service remuneration structure and locate it at SEC or MOF (ref: RuFep) | Cabinet/MoF
Formation | F5 | Create 5 Action Teams for the following areas of effort: * Fiscal policies to address crowding-out effect and other policies to support development of the local capital markets * Choice international investment destination [key deliverables is to secure MSCI rating (ToRs on p6) and propose financial hub model - reMauritus/Abu Dhabi/Seychelles. etc] * Changes to SEC funding model and enhance capacity for SEC to be able to achieve full functionality required under the CMMP * Product Development * Capacity Building [regulators,market players, investing public, etc] | Cabinet/MoF
Formation | F6 | Seek donor support for financing and staffing | MoF/CMWG
Formation | F7 | Orientation and development of the Monitoring & Evaluation Framework: * Orientation walk-through of the CMMP * Monitoring & Evaluation Framework development and capacity building programme | CMWG/MoF*
Formation | F9 | Sensitisation programme/workshop of CMMP to Implementing Partners (includes members of the Action Teams & institutions with assigned tasks in CMMP) | CMWG
Formation | F10 | Develop detailed workplans & budgets for the various broad tasks in the Implementation Plan | CMWG/Action Teams
Formation | F11 | Create and maintain a database consisting of capital markets benchmark data to measure implementation impact and progress | CMWG
Formation | F10 | Report implementation progress to the SC quarterly & to Cabinet* | CMWG/MoF*
Formation | F12 | Evaluate Roadmap progress annually and involve external evaluators at end of years 2, 4, 6, 8 and 10 | CMWG
Capacity - Reg | 4.1.1 | Conduct workshop to identify capacity gaps across regulators | MoF, BoZ and SEC | Change to a study
Capacity - Reg | 4.1.2 | Schedule and execute skills development programmes and/or capacity building workshops with international regulators | MoF, BoZ and SEC | [23 empty] | Skills development programmes completed and capacity built to international standards
Capacity - Reg | 4.1.3 | Ensure built capacity is maintained through annual review and continued skills updates | MoF, BoZ and SEC | [23 empty] | Regulator capacity maintained at international levels
Funding -SEC | 4.2.1 | Review current SEC funding policy against its needs and identify shortfall | MoF and SEC | Include a study/benchmark with other regulator models - pros & Cons | [22 empty] | Size of shortfall quantified
Funding -SEC | 4.2.2 | Engage government and market players to develop updated SEC funding mechanism and implement | MoF and SEC | [23 empty] | Sustainable SEC funding in place
Funding -CMO | 4.3.1 | Identify current shortfall in LuSE funding model | SEC and LuSE | propose a wider view of looking at key stakeholders | [22 empty] | Size of shortfall quantified
Funding -CMO | 4.3.2 | Determine scope for additional value addition services as revenue generators, e.g. publishing market research, information dissemination | SEC and LuSE | [23 empty] | New value addition services identified
Capacity - CMO | 4.3.3 | Develop required capacity to implement identified value addition services | SEC and LuSE | [23 empty] | New capacity developed within LuSE
Funding -CMO | 4.3.4 | Implement additional value addition services and revise listing and annual fees | SEC and LuSE | [23 empty] | Sustainable LuSE funding policy in place with lower listing fees
Capacity - CMO | 4.4.1 | Commission study on best-practice for capacity building | SEC and CMAZ | re-cast and state specific areas | [22 empty] | Study completed, best practices identified
Capacity - CMO | 4.4.2 | Identify gaps with existing capital market practitioners - including auditors, advocates, accountants, brokers, bankers, corporate financiers, financial journalists etc. through surveys, workshops | SEC and CMAZ | [23 empty] | Surveys/workshops conducted, capacity gaps identified
Capacity - CMO | 4.4.3 | Identify skills development programmes to bridge knowledge gap and partner with education provider to design curriculum fit for purpose | SEC and CMAZ | [23 empty] | Appropriate skills development programmes identified, education partner found
Capacity - CMO | 4.4.4 | Develop and execute schedule for participating in bridging knowledge gap | SEC and CMAZ | [23 empty] | Capacity- building scheduling developed and executed, capacity built
Capacity - CMO | 4.4.5 | Schedule and execute capacity building maintenance in order to update skills as required | SEC and CMAZ | [23 empty] | Ongoing scheduling and development of skills programme
Audited accounts | 4.5.1 | Provide guidelines on preparing audited accounts to assist limited liability companies with long-term financing compliance needs | SEC and MoF | Abridged version of audited accountants . Include ZICA [Consider a specific activity for IDC SOEs in the master plan e.g. reporting framework | [22 empty] | Guidelines completed, best practices identified
Audited accounts | 4.5.2 | Host workshops to inform companies about auditing guidelines | SEC and MoF | [23 empty] | Guidelines complete and implemented
Investor education | 4.6.1 | Conduct study on public literacy and capital markets views to identify gaps in knowledge and develop educational material | SEC | Include other players, not just SEC. SEC best placed as lead provided they have capacity built | [22 empty] | Study completed, gaps identified and educational material developed
Investor education | 4.6.2 | Schedule and execute public workshops to deliver training material | SEC | [23 empty] | Executed workshop and education programmes and conducted periodic investor education programmes
implementation should have a primary lead
Note on C930: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LuSE is undergoing demut where all these are motiations - not sure if this is the only outstanding issue
Note on C934: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: for who??
Note on C936: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: too broad based like we do not have a concise direction we want to take. Consultants should have attempted to identify some skills deficit like financial analysis, fund manager, new areas like fintech supervision, green finance related skills, RBS interventions, etc
Note on C939: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: not quite agree - perhaps what would make sense is take say SOEs and register them so they comply with continuing obligations
Note on C940: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: really at a loss but again see above comment
Note on D925: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: we must move away for multiple owners and instead assign say the capacity building Action/Task Team Reply: Also, Consultants were privy to ICA report surely that report should have been referenced in here e.g. why do a workshop when we have a report that recommends key steps - address funding model; recruit more staff and re-organise the Commission